📄 Pickelton Backend Project Plan (Java - Spring Boot)

🎯 Goal (MVP)

Build a production-ready backend where:

- Users authenticate

- Clubs exist

- Tournaments are created

- Players register

- Matches are played

- Leaderboard works

🧱 System Modules

auth

user

club

tournament

registration

match

leaderboard

config

security

common

👥 Team Structure

🔥 Rule

- One person controls DB schema (Team Lead)

- Others follow schema + API contract strictly

👨‍💻 Person 1 — Auth + User + Club

📦 Modules

- auth

- user

- club

🗄️ Tables

users

clubs

club_members

🛠️ Tasks

🔐 Auth

- User entity

- Register API

- Login API

- Password hashing (BCrypt)

- JWT token generation

- JWT filter (Spring Security)

👤 User

- Get profile API

- User DTO

🏟️ Club

- Create club

- Join club

- List clubs

- Role system (ADMIN / MEMBER)

📡 APIs

POST /auth/register

POST /auth/login

GET /users/me

POST /clubs

POST /clubs/{id}/join

GET /clubs

✅ Output

- Working authentication system

- Users stored in DB

- Club system functional

👨‍💻 Person 2 — Tournament + Registration

📦 Modules

- tournament

- registration

🗄️ Tables

tournaments

registrations

🛠️ Tasks

🏆 Tournament

- Tournament entity

- Create tournament

- List tournaments

- Get tournament details

- Validate:

  - creator = user

  - optional club_id

📝 Registration

- Register for tournament

- Prevent duplicate registration

- Slot limit validation

- Registration status

📡 APIs

POST /tournaments

GET /tournaments

GET /tournaments/{id}

POST /tournaments/{id}/register

✅ Output

- Tournament system working

- Registration system working

- Slot validation implemented

👨‍💻 Person 3 — Match + Leaderboard

📦 Modules

- match

- leaderboard

🗄️ Tables

matches

🛠️ Tasks

🎾 Match

- Create match

- Assign players

- Update score

- Set winner

- Add round field

📊 Leaderboard

- Compute wins/losses

- Rank players

- Tournament leaderboard API

📡 APIs

POST /matches

PATCH /matches/{id}/score

GET /tournaments/{id}/leaderboard

✅ Output

- Matches working

- Score updates working

- Leaderboard functional

👑 Team Lead Responsibilities (You)

🛠️ Tasks

🧱 Setup

- Create Spring Boot project

- Setup folder structure

- Setup DB connection (Supabase)

- Initialize repo

🗄️ Database

- Define schema

- Maintain consistency

- Approve changes

🔗 Integration

- Merge modules

- Fix API mismatches

- Ensure full flow works

🚀 Deployment

- Deploy backend

- Configure environment variables

- Test production APIs

🔗 Dependency Flow

Auth → User → Club

↓

Tournament → Registration

↓

Match → Leaderboard

📅 Timeline

Week 1 — Foundation

- Auth complete

- DB setup done

- Club APIs ready

Week 2 — Core

- Tournament APIs

- Registration system

Week 3 — Gameplay

- Match APIs

- Leaderboard

Week 4 — Final

- Integration

- Deployment

- Bug fixing

⚙️ Git Workflow

main → stable

dev → integration

feature/auth

feature/tournament

feature/match

⚠️ Rules

- One DB schema owner

- Same naming conventions

- Use DTOs (no direct entity exposure)

- Test APIs daily

- Integrate early

🚨 Risks

- Auth delay blocks everything

- DB mismatch breaks integration

- API mismatch causes failures

🧠 MVP Scope

✅ Build Now

- Auth

- Clubs

- Tournaments

- Registration

- Matches

- Leaderboard

❌ Later

- Payments

- Feed system

- Image uploads

- Analytics

🔥 Final Product Vision

Pickelton =

Auth

+ Clubs

+ Tournaments

+ Matches

+ Leaderboard

Later:

+ Feed

+ Payments

+ Analytics

📄 PICKELTON FRONTEND PLAN (Next.js)

🎯 Goal

Build a scalable web app (Next.js) that:

- connects to your Spring Boot backend

- supports tournaments, matches, clubs

- is structured for team development

- can later extend to mobile (Expo)

🧱 TECH STACK

- Framework → Next.js (App Router)

- Language → TypeScript

- Styling → Tailwind CSS

- API calls → Axios / fetch

- State (basic) → React state (later Zustand if needed)

🧩 PROJECT STRUCTURE (FINAL)

pickelton-web/

├── app/

│    ├── (auth)/

│    │    ├── login/page.tsx

│    │    └── signup/page.tsx

│    ├── dashboard/page.tsx

│    ├── clubs/

│    │    ├── page.tsx

│    │    └── [id]/page.tsx

│    ├── tournaments/

│    │    ├── page.tsx

│    │    ├── create/page.tsx

│    │    └── [id]/page.tsx

│    ├── matches/

│    │    ├── page.tsx

│    │    └── [id]/page.tsx

│    ├── leaderboard/

│    │    └── [id]/page.tsx

│    ├── profile/page.tsx

│    └── layout.tsx

│

├── components/

├── services/

├── hooks/

├── types/

├── utils/

└── styles/

📄 CORE PAGES (MVP)

🔐 Auth

- /login

- /signup

🏠 Dashboard

- /dashboard

- Shows:

  - upcoming tournaments

  - quick actions

🏟️ Clubs

- /clubs

- /clubs/[id]

Features:

- view clubs

- join club

🏆 Tournaments

- /tournaments

- /tournaments/create

- /tournaments/[id]

Features:

- list tournaments

- create tournament

- view details

- register

📝 Registration

👉 inside tournament page

🎾 Matches

- /matches

- /matches/[id]

Features:

- view matches

- update score

📊 Leaderboard

- /leaderboard/[id]

👤 Profile

- /profile

🎨 UI COMPONENTS (REUSE THESE)

From your existing project:

- CourtCard → matches/tournaments

- GroupCard → clubs

- Navigation → layout

👉 Don’t rewrite—reuse and adapt

🔗 API LAYER (IMPORTANT)

Create:

services/api.ts

Example:

import axios from "axios";

export const api = axios.create({

baseURL: "http://localhost:8080",

});

Example API usage:

export const getTournaments = async () => {

const res = await api.get("/tournaments");

return res.data;

};

🔐 AUTH HANDLING

- Store JWT in:

  - localStorage (simple)

- Add interceptor:

api.interceptors.request.use((config) => {

const token = localStorage.getItem("token");

if (token) config.headers.Authorization = `Bearer ${token}`;

return config;

});

👥 TEAM SPLIT (FRONTEND)

👨‍💻 Person 1 — Auth + Layout

- login/signup pages

- navbar

- route protection

👨‍💻 Person 2 — Clubs + Tournaments

- club pages

- tournament pages

- registration UI

👨‍💻 Person 3 — Matches + Leaderboard

- match pages

- score UI

- leaderboard UI

⚙️ DATA FLOW

User Action → Next.js UI → API call → Spring Boot → DB → Response → UI update

📅 EXECUTION PLAN

🥇 WEEK 1

- Setup Next.js

- Create structure

- Auth pages

- Navigation

🥈 WEEK 2

- Clubs + tournaments UI

- API integration

🥉 WEEK 3

- Matches + leaderboard

- Full integration

🏁 WEEK 4

- UI polish

- Bug fixing

- Deployment

⚠️ RULES

- No hardcoded data

- Use API layer only

- Keep pages separate from components

- Reusable components only

- Keep UI simple first

🚨 COMMON MISTAKES

- ❌ Mixing logic in components

- ❌ No folder structure

- ❌ No API layer

- ❌ Trying to perfect UI first

🧠 FINAL ARCHITECTURE

Next.js (Frontend)

↓

Spring Boot (Backend)

↓

PostgreSQL (Supabase)